## Sheet1
Trail Skills College Tasks and Timelines Worksheet
Months prior to TSC | Task Definitiion | Estimated Cost of Task | Completed
Planning Team/Logistics
6 | Identify a TSC coordinator | 0 | FALSE
6 | Identify Forest Service lead responsible for the meetings management package, if necessary. |  | FALSE
6 | Finalize TSC date and theme, announce on Forest and Partner websites and social media streams. |  | FALSE
5 | Finalize budget (including registration costs and sponsorship goals, instructor cost, classroom rates, lodging rates, etc.) |  | FALSE
4 | Start meetings management package process, if required.This requires knowing cost of travel, GS level and location of the training. |  | FALSE
3 | Submit meetings management package to regional leadership, if required. |  | FALSE
3 | Set up TSC registration system, website, and app (Finalize and make any changes of draft TSC registration website before sending it out to possible participants.) |  | FALSE
2 | Ship/order lanyards/chums and reusable bags |  | FALSE
1 | Close TSC registration. This gives facilitators and kitchen staff some time to see what they need resource wise. |  | FALSE
1 | Work with Host location on catering plan |  | FALSE
1 | Finalize on-site logisitics: registration desk, off-site events |  | FALSE
| scholarship recipient sign up for concurrent session hosts |  | FALSE
| scholarship luncheon? |  | FALSE
1 | Finalize program on an app (if used) |  | FALSE
2-3 week | Final numbers to event site for food and beverage |  | FALSE
1-2 weeks | Print name tags, room signs, other signs (will need someone on site to verify sign needs) |  | FALSE
| sponsor and exhibitor recognition posters |  | FALSE
| scholarship recipient poster |  | FALSE
Post Event | Pay Instructors/contractors (Paypal or other direct deposit system preferred) |  | FALSE
Post Event | Send Feedback survey or after action survey to see where next year’s event can be improved. |  | FALSE
| Total Estimated Cost for Planning and Logistics: | 0
Program Team
5 | Send out poll gauging interest in certain courses. |  | FALSE
5 | Identify potential instructors and backup instructors |  | FALSE
5 | Develop call for proposals in Google Forms (or similar) |  | FALSE
5 | Invitations/outreach to keynote speakers |  | FALSE
4 | Call for proposal submissions soft close |  | FALSE
3 | Call for proposal submissions hard close |  | FALSE
3 | Assign proposal reviewers |  | FALSE
2 | Program committee review complete |  | FALSE
2 | Program selection complete, presenters notified |  | FALSE
2 | Email sent to non-selected presenters (waitlist) |  | FALSE
2 | Determine off-site/after hours activities |  | FALSE
2024-01-02 | Determine CEU credit offerings |  | FALSE
1 | Send Presenter 101 information |  | FALSE
2024-01-02 | Solicit raffle items |  | FALSE
| Set up raffle plan/flow |  | FALSE
| Total Estimated Cost for Programs: | 0
Field Workshop Team
5 | Identify potential field workshop locations |  | FALSE
4 | Contact site managers and partners |  | FALSE
2 | field workshop descriptions |  | FALSE
2 | Publish field workshops on website/app |  | FALSE
2 | Coordinate Transportation, tools, logistics |  | FALSE
5 | Award process and timeline |  | FALSE
4 | Share Call for Nominations |  | FALSE
3 | Deadline Call for Nominations |  | FALSE
2 | Deadline to review awards nominations |  | FALSE
2 | Confirm award recipients |  | FALSE
2 | Notify award recipients (8 weeks in advance) |  | FALSE
2 | Order award plaques |  | FALSE
2 | Contact award recipients about poster/display |  | FALSE
2 | Notify national leadership award recipient |  | FALSE
2 weeks | Awards onsite |  | FALSE
| Total Estimated Cost for Field Workshops: | 0
Scholarship Team
5 | Scholarship process and timeline |  | FALSE
4 | Update Announcement/Request Letter (include question in form if okay with promotion of receiving scholarship) |  | FALSE
3 | Post/Send out Announcement |  | FALSE
2 | Deadline For Applications |  | FALSE
2 | Deadline to review scholarship applications |  | FALSE
2 | Scholarship recipients notified |  | FALSE
2 weeks | Scholarship experience on-site |  | FALSE
2 weeks | Mail/venmo $$ to recipients |  | FALSE
| Total Estimated Cost for Scholarships: | 0
Sponsorship Team
6 | Sponsor strategy and outreach; sponsor guide |  | FALSE
6 | Add potential sponsors and planning team contact |  | FALSE
4 | Develop sponsor guide |  | FALSE
4 | Begin sponsor outreach and confirmation |  | FALSE
3 | Meet with potential sponsors during site visit |  | FALSE
2 | Outreach for raffle/auction donations |  | FALSE
1 | Invoices to confirmed sponsors |  | FALSE
1 | Make sure we have all sponsor logos |  | FALSE
1 | Sponsor communication and coordination |  | FALSE
1 | Outreach to sponsors about booth/table needs |  | FALSE
2 weeks | Sponsor for on-site signs |  | FALSE
2 weeks | Sponsor for TSC give-aways |  | FALSE
| Total Estimated Cost for Sponsorship: | 0
| Total Estimated Cost for Trail Skills College: | 0